## Sheet1
|  | Antonio | Matt | Harry | Collaborative | DESIGN | AXI4 | Registers | SPI
Mon (5/11) |  |  |  |  | make scheduled plans / update reqs | GOALS | (a1) Read Channels | (b1) create load register module | (c1) Baud Rate Generator
Tues (5/12) |  | Expected: a1, Actual : a1 | Expected: b1, Actual: b1 | Expected:c1, Actual:c1 |  | THIS | (a2) Write Channels | (b2) create registers | (c2) clk polarity / phase implementation
Wed (5/13) |  | Expected: a2, Actual: a2 | Expected: b2, Actual: b2 | Expected:c2, Actual:c2 |  | WEEK | (a3) Testing | (b3) connect optional fifo registers | (c3) shift register
Thurs (5/14) |  | Expected: a3, Actual: a3 | Expected: b3, Actual: b6 | Expected:c3, Actual:c3 |  |  | (a4) Connect with registers | (b4) test connection to AXI4 | (c4) test receive / transmit
Fri (5/15) | cross-review | Expected: a4, Actual: a3 | Expected: b4, Actual: b8 | Expected:c3, Actual:c3 | assure design of AXI4 to registers operating as required |  |  | (b5) test read/write on both sides | (c5) test pin interface
Sat | [7 empty] | (b6) implement TOW requirement | (c6) loopback mode
Sun | [7 empty] | (b7) implement FIFO option conditions | (c7)master-slave mode
Mon (5/18) |  | Expected: a4, Actual: a3 | Expected: b5, Actual: b7, b8 | Expected:c4, Actual:c4,c5,c6 | make plans to finish SPI and begin verification |  |  | (b8) test internal write behavior | (c8)LSB,Manual Slave Select
Tues (5/19) |  | Expected: b3, Actual | Expected: b5, Actual: b7, b8 | Expected:c5, Actual:c7 |  |  |  |  | (c9) Status control
Wed (5/20) | cross-review | SPI | Expected: b4 | Expected:c7 | begin system testing
Thurs (5/21) |  |  | Expected: b5 | Expected:c8 | TESTING
Fri (5/22) |  |  | Expected: b5 | Expected:c8 | TESTING